## Opeining Steps
Restaurant Business: the beginning.
The Building Blocks to Opening Day:
The order may vary slightly. Be sure to include each on your planning calendar:
The initial meeting- Begin the Journey
Review and communicate the plan
Allocate resources and who will own what tasks
Real Estate Analysis, what is needed?
Select a Site
Letter of Intent
Review your lease
Architectect
Business Setup Checklist
These are the general business tasks that you will need to complete before progressing much more towards your opening date.
Signed Lease
Now that you’ve secured real estate it’s time to step it into high gear!
Order Equipment
Map Trade Area
Drive your delivery area and map the boundaries.
Submit For Permit
Bid A Contractor
Schedule your personal training
Training to prepare for managing a business should be at least 4 weeks long and should be completed by at approximately 6 weeks prior to opening.
Begin Construction
Permits in hand, construction contract signed construction begins!
Operations Meeting
Meet to discuss the calendar to opening day.
Marketing Confirmation
Create a grand opening marketing campaign, you are on your way to starting your grass roots advertising campaign.
A marketing Calendar for 60 to 90 days needs to be in place
Train For Your Role
Include training for key player(s)
Construction Sign Off
Construction is complete, all equipment is installed, and an occupancy permit has been issued
Creating the Team. Interviewing, Selection, Training
Keys, security codes and First Order
You’ll need to receive your first food order; everything you need to do community tastings before opening day.
Confirm Readiness to Open
Checklists, Double checks.
Pre-Opening Gala. By invitation only. 2 Evenings of practice, community and complimentary food.
Grand Opening Day!
Supplemental - Organizing Your Business Details
These will be items to include on your planning calendar.
Incorporation, LLC, Partnership?
________________________ ___________________ _________________________
Licenses: City, County, State
________________________ ___________________ _________________________
Banking, Accounts with each purpose
________________________ ___________________ _________________________
Accounting
________________________ ___________________ _________________________
Payroll
________________________ ___________________ _________________________
Insurance (Delivery requires specialty)
________________________ ___________________ _________________________
Financing / Funding
________________________ ___________________ _________________________
Accounts Receivable
________________________ ___________________ _________________________
Get a Phone Number
________________________ ___________________ _________________________
Vendors
Equipment, Food, Services, Marketing, Financing & Leasing,
________________________ ___________________ _________________________
________________________ ___________________ _________________________
________________________ ___________________ _________________________
________________________ ___________________ _________________________
________________________ ___________________ _________________________
________________________ ___________________ _________________________
________________________ ___________________ _________________________
________________________ ___________________ _________________________
________________________ ___________________ _________________________
________________________ ___________________ _________________________
________________________ ___________________ _________________________
________________________ ___________________ _________________________
________________________ ___________________ _________________________
Supplemental - As soon as lease is signed for location..
These items should be done as soon as you have a signed lease.
Secure phone #_______________________________
Name of phone co.___________________________________________
Set up voicemail
Arrange for website
Bind insurance policy
Name of insurance co. _____________________________________________________
Contact info:_____________________________________________________________
Order heavy equipment package
Arrival Information _______________________________________________________
Order phone system
Name of phone system and contact info:
________________________________________________________________________
Order POS system
Details__________________________________________________________________
________________________________________________________________________
Order exterior sign
Sign company and estimated arrival date:
________________________________________________________________________
Sign up for Payroll Service
Start Hiring Process for Store Manager
Order all pre open/grand opening marketing material (no later than 10 weeks from opening day)
Supplemental - Build the Team & Create The Sales
Approximately 8 to 10 weeks from opening day, you begin the count down.
This area will take more time than you might realize. Include these activities on your planning calendar
Marketing materials can easily take 8 weeks to design, print and deliver if larger volumes ordered
These are NOT required but offer improved chance for success. There are many more options at http://www.michaelhartzell.com
Create Sales / Marketing
List of marketing materials: (order in advance)
Menus
Magnets
Doorhangers
Coming Soon
Grand Opening
Sample Night, Guest on the House
Banner
Coming Soon
Grand Opening
Business cards with the store’s address and phone number
Hand outs, Flyers
Promo items; Frisbees, pens, note pads
Direct Mail Coupons and offers
Job Aides for Training / Coaching staff
Door hangers
pre 2 weeks |  | ‘Coming soon’ door hangers (10 to 20 thousand)
Grand open wk |  | Grand Opening’ door hangers starting opening week. Continue for four weeks.
Direct Mail
pre 1 week |  | Advo "free invitition" / now hiring
pre 3 weeks |  | Advo Coming Soon / Now Hiring / with grand opening offers
Grand open wk |  | Advo on opening day – Grand opening piece – Opening week
pre 2 weeks |  | Val Pak coming soon / now hiring with offers
Grand open wk |  | Send business mailings Opening week
Post grand open wk |  | Direct Mail Postcards - Now open - targeted
mirror above |  | Select around elementaries for targeted marketing with giant postcards.
Newspapers
Pre 1 week |  | Coming soon ad, map, service area
Grand Open wk |  | Grand opening ad, map, service area,
Business Visits if opened for lunch daily
start pre 2 weeks |  | 50 daily visits by owner or managers (need a team to execute)
Product Sampling (Tastings)
5 days pre-open |  | As many samplings as possible; (what primary menu item can be shared?)
Minimum of four before opening.
Banner Waving
pre 2 weeks |  | ‘opening soon’ selected days 2 weeks before open at busy intersections
Grand open wk |  | ‘Now open’ everyday opening week.
Select days first month of business.
Community Bulletin Boards
Grand Open wk |  | ‘Now open’ flyers posted opening week
|  | Online / Internet |  |  | All point to website
pre 8 weeks |  | Myspace
pre 8 weeks |  | Facebook
pre 8 weeks |  | LinkedIn
pre 8 weeks |  | Twitter
pre 8 weeks |  | eBay
pre 8 weeks |  | Entertainment Book
pre 8 weeks |  | Restaurants.com |  | (optional)
pre 8 weeks |  | Free Classified Online Ads
pre 8 weeks |  | Youtube
pre 8 weeks |  | Website
Guerrilla Tactics
Grand open wk |  | Parade of cars with car-tops prior to Open
Grand open wk |  | “Pre-Open Gala" the previous days before Open
Grand open wk |  | Early a.m...... hand out flyers at office buildings
Grand open wk |  | Leave coupons at transit stops
Grand open wk |  | Windshield store parking lots
Grand open wk |  | New Customer Kits to hand out in delivery area & on deliveries until supply runs out
Phone Power
pre 2 weeks |  | Clip and Call out of local Paper
PRESS
Grand open wk |  | Press releases to all area papers/newsletters
Grand Open wk |  | Online press releases
Community
Pre-Grand open |  | Chamber of Commerce, set up Grand opening ribbon cutting ceremony with Mayor
Post Opening |  | “Thanks for being one of the first” mailer
pre 1 week |  | Libraries, Community Centers, Sports Centers, combine with business visits
Recruiting
pre 45 days |  | Place job orders employment agencies, state & private
pre 45 days |  | Letters to all area church pastors
pre 45 days |  | Newspaper ads
pre 45 days |  | Post Now Hiring flyers at area college’s bulletin boards
pre 45 days |  | High school counselors – letters ask for referrals
pre 45 days |  | High school clubs – DECA, FBLA…
pre 45 days |  | Recruiting Materials Needed
pre 45 days |  | Banner
“now hiring”
“coming soon”
Applications available for possible candidates outside front door
pre 45 days |  | Window posters:
Now Hiring
Coming soon
pre 45 days |  | Website online for application and contact info
pre 45 days |  | Applications
pre 2 weeks |  | Employment packets I9, W4, Employee information sheet
pre 2 weeks |  | Employee orientation packet
pre 45 days |  | Advertisement scripts for newspapers and online
Pre-Opening
Grand open wk |  | Family Day for Staff
Grand open wk |  | Employee Orientation for new staff
Grand open wk |  | Delivery area tour
Grand open wk |  | Pre-Opening Day Gala - distribute 200 invitations for complimenatary food (specific time)
Hiring goal:
pre 45 days |  | 1.5 staff for every $1.000 in sales for week projected.